## Event Details
EVENT DETAILS
| Event Title | Protein Conference | Date | 2022-03-22
| Venue Name | Dalby Events Centre | Contact | Justin Heaven
| Venue Address | 54 Nicholson St, Dalby | Sponsorship
|  | Details | Supplier/Contact | Invoice
Venue | Venue | Dalby Events Centre
Deposit
Final Invoice Paid
Map
Décor
Food and Alcohol | Catering
Alcohol
Cocktails
Crockery
Glassware
Invitation | Save the Date
Invitation
Guest list
RSVP Date
RVSP Form
Entertainment | Band/music
Performing act
MC
Marketing | Social Media
Website
Branding
Signage/Banners
Media Release/Invite
Powerpoint Presentation
Printing | Program
Menu Cards
Place Cards
Seating Chart
AV/Sound | PA/sound system
Screen
Lighting
Laptop
Travel | Bus
Accomodation
Car Hire
Parking
Flights
Sponsorship | Sponsor
Sponsor Value
Invoiced
Imaging | Photography
Videography
Risk Assessment | Risk Assessment

## Event To-Do List
EVENT TO-DO LIST TEMPLATE
| EVENT TITLE |  | DATE(S) |  | LOCATION
| TASK TITLE | PERSON RESPONSIBLE | DATE DUE | DATE COMPLETED | COMMENTS
| Create tickets on website | Katie | 2022-11-20 | 24/11/2022
| Find Sponsors | Justin | 2022-11-20
| Sponsorship Perspectus complete | Annie-Lou | 2022-11-28 | 2022-11-29 | Uploaded on Website
| Save the Date | Annie-Lou | 2022-12-04 |  | Send out to Database & on Facebook
| Invitaitons letters to Speakers | Justin | 2022-12-05
| Sponsors Logos on website | Codie | 2023-01-10
| Exihibitor booth design/Floor Plan | Codie | 2022-12-12
|  | Codie | 2022-12-19
|  | Codie/Katie | 2022-12-19
|  | Codie | 2022-12-19
| Coffee Cups with Sponsor logo | Codie | 2023-01-16 |  | https://www.zazzle.com.au/simple_minimal_business_logo_custom_paper_cup-256123411557241468
| Notepads - TSBE? | Codie | 2023-01-16
| Collect merchandise for satchels | Codie | 2023-01-16 |  | Recognition Plus
| Quote and order Satchels | Codie | 2023-01-16 |  | Get a quote for a satchel with logos
| Quote and order Lanyards | Codie | 2023-01-16
| Social media Plan for the event - before, During and after | Annie-Lou | 2023-01-16 |  | Rolling promotion of speakers announced on Social each week.
| Program on the website | Codie | 2023-01-16
| Quote/Book a bus for site tour | Codie | 2023-01-16 |  | TBC
| Sort out catering/beverage for networking | Codie | 2023-01-30
| Coffee Cart - Get a quote | Codie | 2023-02-20 | 2023-01-13 | Coffee Cart booked, logo on coffee carts and cups based on Sponsor
| Stage design | Codie | 2023-03-06 |  | Lectern and armchairs for panel disucssions
| Sign for the Lectern | Codie | 2023-03-13
| Napkins with Sponsor logo | Codie | 2023-03-13 |  | https://www.zazzle.com.au/navy_branded_custom_business_logo_promotional_napkin-256376652240921906
| Design and print program | Codie | 2023-03-13 |  | Sponsors adverts, speakers bio and program,
| Powerpoint presentations | Codie | 2023-03-20
| Media Release invitation | Annie-Lou/Katie
| Confirm Speaker - Finalise any requirements/Travel | Codie | 2023-03-01
| Finalise Budget | Codie | 2023-03-20
| Send reminders to guests and sponsors | Codie | 2023-03-20
| Confirm attendee numbers for venue & catering | Codie | 2023-03-25
| Mc notes for Justin | Codie | 2023-03-25
| Speaker Bios | Codie
| Catering Boxes |  |  |  | Encours
Sign for Lecturn

## Sponsors
EVENT SPONSOR
|  | Company | Contact |  |  | Invoice | Logo on Collateral | Email about package elements | Includes
Conference Partner | 4000 | APIAM Animal Health |  | forbes.corby@apiam.com.au and cc tony.batterham@apiam.com.au |  | Email sent | Yes
| 4000 | Entegra | Greg McCalman Kimberley Scott | greg@entegra.com.au kimberley@entegra.com.au | 0448 530 440 | Email sent | Yes
| 4000 | Mindaroo | Bruce McConnel | bmcconnel@minderoo.org | 0499 025 118 | Email sent
Twilight Sponsor | 4000 | Agri Talent | Kelli McDougall | kelli.mcdougall@agritalent.com.au>; | 0427 596 000 | Invoiced | Yes | Yes
Industry Sponsor | 3000 | MLA | Rachel Hall Kayla | events@mla.com.au |  | Invoiced | Yes
Coffee Cart Sponsor | 2000 | RSA Contractors | James Schirmer Anna Story | jschirmer@rsa.contractors astory@rsa.contractors | 0407 598 001 | Invoiced | Yes | Yes
Catering Sponsor | 1500 | IOR Caltex Delo | Georgie Hart | georgie.hart@ior-rural.com.au | 0437 383 380 | Invoiced | Yes | Yes
Lanyard Sponsor | 1000 | NAB | Jason Lipp | jason.a.lipp@nab.com.au | 0428 297 250 | Invoiced | Yes | Yes
Site Tour | 4000 | Mort & Co | Sarah Patterson | Sarah.Patterson@mortco.com.au |  |  | Yes | Yes

## Trade Stalls
TRADE STALLS
Site |  | Company | Contact | Email | Attendee | Power | Phone Number | Signed Form | Emailed information | Attendee for Stall | Invoice | PO
1 | No walled | Western Downs Regional Council | Lidewij Koene | Lidewij.Koene@wdrc.qld.gov.au |  |  | 0409 786 759 | Sponsorship | Yes | Yes
2 | No walled | Royal Flying Doctor's Service |  | peter.caswell@reparator.com.au | Libby Gardiner |  |  | Free | Yes | Yes
3 | Deck | Entegra | Kimberley Scott | kimberley@entegra.com.au | Adam Smith |  | +61(0)491149356 | Sponsorship | Yes | Yes
4 | Deck | Apiam |  | forbes.corby@apiam.com.au | Haylee Clifford |  |  | Sponsorship | Yes | Yes
5 | Deck | Agri Talent/Agri Labour | Nick Marchant | nick.marchant@agritalent.com.au |  |  | 0476 884 936 | Sponsorship | Yes
6 | Deck | RSA Contractors | Ann Story | Astory@RSA.contractors | Ann Story |  |  | Sponsorship | Yes | Yes
7 | Deck | Smater Nutrition | Alexandra Aisthorpe | a.aisthorpe@topcountry.com.au | Stephen Aisthorpe Andrew Whyte |  |  | Invoiced | Yes | Yes
8 | Deck |  |  | sarah.patterson@mortco.com.au |  |  |  | Sponsorship | Yes | Yes
9 | Deck | Wideland | Lisa Nicholls | lisa.nicholls@widelandgroup.com.au | Lisa Nicholls | no |  | ?? $1500 | Yes | Yes
10 | Deck | Agtech 360 | Pieter van Jaarsveld | pieter@agtech360.net | Pieter Van Jaarsveld Julian Pollard |  | 0414 886 052 | Invoiced | Yes
11 | Deck | Equipoise Group |  | rob.fraser@fraservaluers.com | Yeonju Jang | No |  | Invoiced | Yes
12 | Deck | West Wind Energy | Thomas Walker | thomaswalker@w-wind.com.au | Carissa Crabtree Fin Griffin | no | 0413 974 984 | Invoiced | Yes
13 | Deck | Green Collar | Kim Mason | kim.mason@greencollar.com.au | Saul Clough Jamie Dennison | yes |  | Paid | Yes
14 | Side | Bugs for Bugs | Dan Papacek | dan@bugsforbugs.com.au | Dan Papacek David Loxley | no | 0427 654 663 | Paid | Yes
15 | Side | Data42/Horse Records |  | info@horse-records.com |  | no |  | Invoiced | Yes
17 | Side | Darling Downs Tarpaulins | Michael Ryan | michael@ddt.com.au |  |  | 07 4634 2166 | Paid | Yes
16 | Side | Natural Capital Co | Natalie Williams | nat@natcapco.com.au |  | Yes |  | Sent to Bev | Yes
18 | Side | MLA |  | events@mla.com.au | Rachel Hall | No | 0459978244 | Sponsorship | Yes
19 | Side | Dom Distribution |  |  |  | NO |  | Sent to Bev | Yes
20 | Side

## Budget
EVENT BUDGET |  |  | Profit Goal = $20k
Projected income | 64750 |  |  | Actual income |  |  | 52990
Projected expenses | #REF! |  |  | Actual expenses |  |  | 31101.05
Projected Profit | #REF! |  |  | Profit |  |  | 21888.95
CATEGORY |  | COST P/U | QTY | PROJECTED INCOME | COST P/U | QTY | ACTUAL INCOME | COMMENTS | Invoiced
Sponsorship |  |  |  | 43750 |  |  | 32000
Conference Partner |  | 4000 | 6 | 24000 | 4000 | 3 | 12000 | Entegra, APIAM, Farmed Well | Yes
Industry Sponsor |  |  |  |  | 3000 | 1 | 3000 | MLA | Yes
Twilight Event Sponsor |  | 4000 | 1 | 4000 | 4000 | 1 | 4000 | Agri Talent & Agri Labour | Yes
Coffee Cart Sponsor |  | 2000 | 1 | 2000 | 2000 | 1 | 2000 | RSA Contractors | Yes
Catering Sponsor |  | 1500 | 1 | 1500 | 1500 | 1 | 1500 | IOR Caltex Delo | Yes
Lanyard Sponsor |  | 1000 | 1 | 1000 | 1000 | 1 | 1000 | NAB | Yes
Site Tour Sponsor |  |  |  |  | 4000 | 1 | 1000 | Mort & Co | Yes
Trade Stall Package |  | 750 | 15 | 11250 | 750 | 10 | 7500 |  | Yes
Lawn Booth - Wideland |  |  |  |  | 1500 | 1 | 1500 | Wideland | Yes
Ticket Sales |  |  |  | 21000 |  |  | 20990
Members |  | 130 | 100 | 13000 | 130 | 116 | 15080
Non Members |  | 160 | 50 | 8000 | 160 | 88 | 14080
Complimentary |  |  |  |  | $ 0.00 | 37 | 0
Total Conference | [5 empty] | 241
Site Tour | [5 empty] | 51 | 710
CATEGORY |  |  |  | PROJECTED EXPENSES |  |  | ACTUAL EXPENSES | COMMENTS | Invoice
Conference | SUBTOTALS | Cost | Qty | 12166 | Cost | Qty | 26374.35
Venue Hire & Set up fee |  | 550 | 1 | 550 | 1072 | 1 | 1072 | Western Downs Regional Council | Sent | #REF!
Morning Tea |  |  |  |  | 8.8 | 250 | 2200 | Thyme to Plate | Sent
Lunch - Norish Bowls |  |  |  |  | 15.4 | 250 | 3850 | Thyme to Plate | Sent
Afternoon Cakes |  |  |  |  | 8.8 | 150 | 1320 | Thyme to Plate | Sent
Drinks (2 waters and 1 Juens/soft drink pp) |  |  |  |  | 3.3 | 800 | 2640 | Thyme to Plate | Sent
Catering staff for events | [6 empty] | 1980 | Thyme to Plate | Sent | #REF!
AV Equipment |  | 2000 | 1 | 2000 | 1707.75 | 1 | 1707.75 | Visual Focus | Sent
Photography & Videography |  | 1500 | 1 | 1500 |  |  | 1550 | Salt Studio | Sent
Coffee |  | 4 | 300 | 1200 | 3 | 266 | 798 | C8H10N4O2 Caffeine | Sent
Espresso & Tea |  |  |  |  | 2 | 19 | 38 | C8H10N4O2 Caffeine | Sent
Espresso Bar Hire & Staff |  | 60 | 8 | 480 | 50 | 7.5 | 375 | C8H10N4O2 Caffeine | Sent
Cofee Van Hire & Travel |  |  |  |  | 100 | 1 | 100 | C8H10N4O2 Caffeine | Sent
Coffee Cups |  | 1.392 | 500 | 696 | 1.97 | 500 | 985 | Recognistion plus | Sent
Coffee Lids | [5 empty] | 1 | 0 | Recognistion plus
Facebook Promo |  | 2000 |  | 2000
Tote bags |  | 7.48 | 500 | 3740 | 8.23 | 250 | 2057.5 | Recognistion plus | Sent
Protein PVC Sign |  |  |  |  | 57 | 1 | 57 | Signs on Time | Sent
Coffee Cart Decal |  |  |  |  | 57 | 1 | 57 | Signs on Time | Sent
Stageing |  |  |  |  | 380 | 1 | 380 | Tayla Made | Sent
A6 Name Tags - |  |  |  |  | 0.90103 | 300 | 270.31 | Snap Printing | Sent
A4 Booklets |  |  |  |  | 2.868 | 250 | 717 | Snap Printing | Sent
PVC Foamboard |  |  |  |  | 68.65 | 1 | 68.65 | Snap Printing | Sent
A4 Table Cards |  |  |  |  | 3.4724 | 25 | 86.81 | Snap Printing | Sent
Label Stickers |  |  |  |  | 0.29448 | 250 | 73.62 | Snap Printing | Sent
Booth Hire |  |  |  |  | 3990.71 | 1 | 3990.71 | Range Event Hire | Sent
Networking Event | SUBTOTALS |  |  | 5750 |  |  | 4726.7
Drinks |  | 25 | 150 | 3750 | 1247.9 | 1 | 1247.9 | Windsor Hotel
Catering |  | 2000 | 1 | 2000 | 14.52 | 190 | 2758.8 | Thyme to Plate | Sent
Bar Staff |  |  |  | 0 | 720 | 1 | 720 | JTW Cleaning & Bar Services | Sent

## YES_Seating Chart (hidden)
Seat No. | Organization Name |  | First Name | Last Name | Email | P.O.B | RSVP | Dietary | RSVP / Dietary Notes | TALLY
| AERgO International PTY LTD | 1 | Jamie | Kennedy | jamie@aergo.com.au |  | YES |  |  | YES | 92 | DIETARY | 0
| Western Downs Regional Council | 2 | Debbie | McVeigh | paul.mcveigh@wdrc.qld.gov.au |  | NO
| AERgO International PTY LTD | 2 | Alison | Kennedy |  |  | YES |  |  | NO | 14
| ANZ | 1 | Marcus | Barnard | marcus.barnard@anz.com |  | YES
| ANZ | 2 | Derek | Sams | derek.sams@anz.com |  | YES
| APLNG/Origin Energy | 2 | Rebecca | Pickering |  |  | YES
| APLNG/Origin Energy | 1 | Fraser | Power | fraser.power@aplng.com.au |  | YES
| Councillors - TRC Councillors | 10 | Erin | Kehoe-O'Shea |  |  | YES
| Councillors - TRC Councillors | 9 | James | O'Shea | james.oshea@tr.qld.gov.au |  | YES
| Councillors - TRC Councillors | 3 | Nancy | Sommerfield | nancy.sommerfield@toowoombarc.qld.gov.au |  | YES
| Councillors - TRC Councillors | 15 | Chris | Tait | chris.tait@toowoombarc.qld.gov.au |  | YES
| Councillors - TRC Councillors | 16 | Jane | Tait | jane.tait@toowoombarc.qld.gov.au |  | YES
| FKG | 1 | Gary | Gardner | garyg@fkg.com.au |  | YES | N | 7.11.16
| FKG | 2 | Melissa | Templeman |  |  | YES | N | 7.11.16
| Government | 7 | Deb | Frecklington | nanango@parliament.qld.gov.au |  | YES
| Government | 8 | Jason | Frecklington | Stephanie.Miles@opposition.qld.gov.au |  | YES
| Government | 2 | Dale | Last |  |  | YES |  | MP Shadow Minister for Agriculture, Fisheries and Forestry
| Government | 11 | John | McVeigh | John.j.mcveigh@aph.gov.au |  | YES |  | **Will arrive after the Wonderland Xmas lights approx 7:15pm
12
| Government | 25 | Jeff | Seeney | Callide@parliament.qld.gov.au |  | YES |  | Won't be bringing anyone with him
| Government | 9 | Trevor | Watts | toowoomba.north@parliament.qld.gov.au |  | YES
| Government | 1 | Pat | Weir | condamine@parliament.qld.gov.au |  | YES |  | 16.11.16
| Heritage | 1 | Peter | Lock | Lock.P@heritage.com.au |  | YES |  | 21.11.16
| Heritage | 2 | Jacqui | Lock |  |  | YES |  | 21.11.16
| Hughes et al | 1 | Ben | Hughes | ben.hughes@hughesetal.com.au |  | YES
| Hughes et al | 2 | Chris | Mills |  |  | YES
| InterlinkSQ | 1 | Andrew | Parratt | andrewp@interlinksq.com.au | POB | YES |  | 18.11.16
| IOR Petroleum | 3 | Andrew | Griffiths | Andy.Griffiths@ior.com.au |  | YES
| IOR Petroleum | 4 | Helen | Griffiths |  |  | YES
| IOR Petroleum | 1 | Ross | Mackenzie | ross.mackenzie@ior.com.au |  | YES
| IOR Petroleum | 2 | Anne | Mackenzie | ross.mackenzie@ior.com.au |  | YES
| March IT | 4 | Jacqui | McKenzie | jacqui.mckenzie@marchit.com.au |  | YES
3
| Murdoch Lawyers | 2 | Matthew | Bell | holly@murdochs.com.au |  | YES
| Namoi Cotton | 1 | Jeremy | Callachor | jcallachor@namoicotton.com.au | POB | YES
| Namoi Cotton | 2 | Emma | Callachor |  | POB | YES
| New Hope Group | 1 | Shane | Stephen | sstephan@newhopegroup.com.au |  | YES |  | 21.11.16
| New Hope Group | 2 | Karen | Stephen |  |  | YES |  | 23.11.16
| Oakey Abattoir | 1 | Pat | Gleeson | pgleeson@oakeyabattoir.com.au | POB | YES |  | 21.11.16
| Oakey Abattoir | 2 | Racheal | Gleeson |  | POB | YES |  | 21.11.16
| Ostwald Bros | 2 | Melissa | Kerr |  |  | YES
| Ostwald Bros | 1 | Brendan | Ostwald | brendan.ostwald@ostwaldbros.com.au |  | YES
| Port of Brisbane | 3 | Andrew | Brinkworth | Andrew.brinkworth@portbris.com.au | POB | YES | N
| Port of Brisbane | 1 | Roy | Cummins | Roy.cummins@portbris.com.au | POB | YES | N
| South Burnett Regional Council | 1 | Mayor Keith | Campbell | mayor@southburnett.qld.gov.au |  | NO
| South Burnett Regional Council | 2 | Marion | Campbell | BBarry@southburnett.qld.gov.au |  | NO
| Port of Brisbane | 2 | Peter | Keyte | Peter.keyte@portbris.com.au | POB | YES | N
12 | Roy Cummins
| Port of Brisbane | 4 | Karla | Simpson | Karla.simpson@portbris.com.au | POB | YES | N | 21.11.16
| Power Tynan | 1 | Amanda | Kenafake | ak@powertynan.com.au |  | YES |  | 9.11.16
| QantasLink | 2 | Terry | Bower |  |  | YES |  | 18.11.16
| QantasLink | 1 | Elsa | Dalessio | edalessio@qantas.com.au |  | YES |  | 18.11.16
| QRC | 1 | Hon Ian | Macfarlane | ianmacfarlane@outlook.com |  | YES
| QRC | 2 | Karen | Macfarlane | lynleyp@qrc.org.au |  | YES
| RMA Engineers | 3 | Scott | Graham | scott.graham@rmaeng.com.au |  | YES
| RMA Engineers | 4 | Lauren | Graham | scott.graham@rmaeng.com.au |  | YES
| RMA Engineers | 1 | Jason | Wardle | jason.wardle@rmaeng.com.au |  | YES |  | Won't arrive until 7pm
| Western Downs Regional Council | 1 | Paul | McVeigh | paul.mcveigh@wdrc.qld.gov.au |  | NO
| RMA Engineers | 2 | Shelley | Wardle |  |  | YES |  | Won't arrive until 7pm
| Senex Energy Limited | 1 | Ian | Davies | ian.davies@senexenergy.com.au |  | YES
| Stonestreets Coaches | 1 | Rob | Brown | rob.brown@stonestreets.com.au |  | YES
11 | Peter Keyte
10 | Paul Antonio
9 | Pat Gleeson
| Stonestreets Coaches | 2 | Natalie | Foster | natalie.foster@stonestreets.com.au |  | YES
| Stonestreets Coaches | 3 | Bev | Mules | bev.mules@stonestreets.com.au |  | YES
| Stonestreets Coaches | 4 | Michelle | Mules | michelle.mules@stonestreets.com.au |  | YES
| TAFE Qld SW | 2 | Michele | Berkhout |  |  | YES
| TAFE Qld SW | 1 | Brent | Kinnane | brent.kinnane@tafe.qld.edu.au |  | YES
| TSBE Board | 13 | Mayor Paul | Antonio | paul.antonio@toowoombarc.qld.gov.au | POB | YES |  | 22.11.16
| TSBE Board | 11 | Lisa | France | lisa.france@hatch.com |  | YES |  | 24.11.16
| TSBE Board | 12 | Chad | Freshwater |  |  | YES |  | 24.11.16
| TSBE Board | 19 | Rohan | Gosstray | rohan.gosstray@thechronicle.com.au |  | YES |  | 9.11.16
| TSBE Board | 20 | Andrea | Gosstray |  |  | YES |  | 9.11.16
| TSBE Board | 23 | Rob | Hart | rob.hart@squabillion.com.au |  | YES |  | GU - called to follow up 24.11.16
| Maranoa Regional Council | 5 | Cameron | O'Neil | cameron.oneil@maranoa.qld.gov.au |  | NO
| Maranoa Regional Council | 6 | Partner |  |  |  | NO
8 | Karla Simpson
7 | John Wagner
6 | Jeremy Callachor
| TSBE Board | 24 | Kate | Hart |  |  | YES
| TSBE Board | 7 | Dallas | Hunter | Dallas.Hunter@fkg.com.au | POB | YES | N | 7.11.16
| TSBE Board | 8 | Leonie | Hunter |  | POB | YES | N | 7.11.16
| TSBE Board | 3 | John | Moncrieff | john@calibreadvisors.com.au |  | YES |  | 21.11.16
| TSBE Board | 4 | Anna | Moncrieff |  |  | YES |  | 21.11.16
| TSBE Board | 17 | Stewart | Morland | stewart@ior.com.au |  | YES |  | 21.11.16
| TSBE Board | 18 | Tracey | Morland |  |  | YES |  | 21.11.16
| TSBE Board | 1 | Matthew | Ostwald | Matthew.Ostwald@ostwaldbros.com.au |  | YES
2
| TSBE Board | 21 | Mac | Stirling | lauder@icr.com.au |  | YES |  | 18.11.16
| TSBE Board | 22 | Ann | Stirling |  |  | YES |  | 18.11.16
| TSBE Board | 25 | Joe | Wagner | joe.wagner@wagner.com.au |  | YES |  | 21.11.16
| TSBE Board | 26 | Helen | Wagner |  |  | YES |  | 21.11.16
| TSBE Board | 5 | Gavin | Walton | gavin.walton@cecpl.com.au |  | YES
| TSBE Board | 6 | Liesel | Walton |  |  | YES
| TSBE Staff | 7 | Stacey | Burrell |  |  | YES |  | 8.11.16
| TSBE Staff | 5 | Shane | Charles | shane@tsbe.com.au |  | YES
| Geothermal Industries | 3 | Sean | Ryan | sean@geothermalindustries.com.au |  | NO
| Geothermal Industries | 4 | Partner |  |  |  | NO
| TSBE Staff | 6 | Carmel | Charles |  |  | YES
| TSBE Staff | 1 | Ben | Lyons | ben@tsbe.com.au | POB | YES
5 | Dennis Wagner
4 | Dallas Hunter
| TSBE Staff | 3 | Lance | MacManus | lance@tsbe.com.au |  | YES
| Councillors - TRC Councillors | 5 | Geoff | McDonald | geoff.mcdonald@toowoombarc.qld.gov.au |  | NO
| Councillors - TRC Councillors | 6 | Lisa | McDonald | Claire.McGovern@tr.qld.gov.au |  | NO
| TSBE Staff | 4 | Emily | MacManus |  |  | YES
| TSBE Staff | 2 | Di | Tate |  | POB | YES
| TSBE Staff | 8 | Georgie | Uppington |  |  | YES |  | 7.11.16
| USQ |  | Gavin | Ash |  |  | YES
3 | Ben Lyons
| Wagners | 1 | Denis | Wagner | denis.wagner@wagner.com.au | POB | YES
2
| Wagners | 3 | John | Wagner | john.wagner@wagnerglobal.com | POB | YES
4
2 | Andrew Parratt
1 | Andrew Brinkworth
| AGL | 1 | Clare | Mildren | CMildren@agl.com.au |  | NO |  | 24.11.16 | TBC | 0
| AGL | 2 | TBC | TBC |  |  | NO |  | GU - Clare will confirm name 25.11.16 | TOTAL | 0
| AGL | 3 | TBC | TBC |  |  | NO |  | GU - Clare will confirm name 25.11.16
| AGL | 4 | TBC | TBC |  |  | NO |  | GU - Clare will confirm name 25.11.16
| Western Downs Regional Council | 3 | Ross | Musgrove | ross.musgrove@wdrc.qld.gov.au |  | YES
| Western Downs Regional Council | 4 | Kari | Stephens |  |  | YES
***for seating - Port of Bris folks would like to sit near/with their invitees to their dinner.

## Contacts
Agenda item | Speaker
Opening Address - Acknowledgement of Country
Paul McVeigh - Welcoming Address
Minister Murray Watt |  | Rebecca McDougall Executive Assistant Office of Senator The Hon Murray Watt Minister for Agriculture, Fisheries and Forestry Minister for Emergency Management P: 02 6277 7190 (Canberra) P: 07 3001 8180 (Brisbane) E: ministerwatt.invitations@agriculture.gov.au
Jason Strong MLA – strategic direction |  | kgludman@mla.com.au; events@mla.com.au
Kayla Ludman - Member Services Program Manager P: +61 (2) 9463 9179
Meat & Livestock Australia
Teresa Garcia-Moore, LL.M., Ph.D. (She/Her/Hers) Manager, Science and Impact Food, Beverage and Agriculture Sector Tel +1 479 236 6181 Email teresa.garcia-moore@sustainabilityconsortium.org www.sustainabilityconsortium.org
The Sustainability Consortium |  | SPEAKER - Amy Scoville-Weaver - Director of Retail TSC
Bio-security
| 1. Chief Veterinary of Officer – Federal | Megan Rajic Executive Assistant to Dr Chris Parker Biosecurity Animal Division Department of Agriculture, Fisheries and Forestry 02 6272 3140 ¦ E-mail: Megan.Rajic@agriculture.gov.au
| 2. Chief Veterinary of Officer – State | Allison Crook Queensland Department of Agriculture General Manager - Animal Biosecurity allison.crook@daf.qld.gov.au (04) 2763-2680
| 3. McLean Farms | Franswa Venter Poultry Operations Manager 385 Pittsworth-Felton Road, Pittsworth QLD 4356 PO Box 158, Pittsworth QLD 4356 Australia P:0475208997 F: e: Frans.venter@mcleanfarms.com.au
| 4. Mort & Co | Scott Braund Scott.Braund@mortco.com.au m- 0427 618 622
- Carbon and sustainability
Platforms and systems Carbon explained
Producer example, already implementing and are market forces increasing awareness
| 1. Foodbuy Australia | Kristina Formuzal Foodbuy - Senior Sustainability Manager kristinaformuzal@foodbuy.com.au | Market approach – Woolworthes
Sustainability | 2. Rethink Sustainability | Sharon Denny Queensland Partner ReThink Sustainability Level 15, 240 Queen Street. Brisbane. QLD. 4000. Australia. m: 0447766611 | Sustainability consortium – partners with Woolies
| 3. Sunpork | Dr Robert van Barneveld B.Agr.Sc. (Hon), PhD., RAnNutr., FAICD Group CEO and Managing Director Office: 1/6 Eagleview Place, Eagle Farm QLD 4009 T 07 3908 1440 Mail: PO Box 5950, Manly, QLD 4179 Mobile: 0418 802 462 Email: robert.vanbarneveld@sunporkfarms.com.au | Compass group sustainability manager
| 4. Mort & Co - Predictor Plus | Cameron Best - contacts to follow
- Animal Welfare
Animal surveillance to detect early sickness or decrease in condition/growth
| Animal EYEQ surveillance | Andrew Gray Animal EyeQ Director E - andrew@animaleyeq.com m - (04) 2853-1424 | Research on benefits improved productivity from shedding
Animal welfare | Camm Agriculture | Speaker TBC | New tech or innovation helping
| Minderoo Foundation | Bruce McConnel Minderoo Foundation M +61 499 025 118E bmcconnel@minderoo.org W minderoo.org | What are current producers implementing – Hervey Beef?
| APIAM Animal Health | Jemma Postle Veterinarian – Feedlot APIAM Animal Health | New pain relief or other?
- New Energy – improving efficiencies
Waste to energy
Hydrogen
New energy/project | Wasco Energy | Stuart Pratt Business Development Officer Wasco (Australia) Pty Ltd m - 0457 394 768 E - stuart.pratt@wascoenergy.com.au | New energy solutions
| Optinmal Group | Steve Budden Optimal Group Sales Manager Queensland and Resources M +61 413 410170 E steve.budden@optimalgroup.com.au | What are producers implementing? including cost compared, ROI improved efficiencies
| JBS | Sam Churchill Group Manager Sustainability JBS Australia
| CSIRO | TBC if available??
- Improved production practices
| 1. Entegra Sheds | Greg McCalman Entegra Company Lead 0448 530 440 greg@entegra.com.au | New shedding systems, research and improved productivity gains
Production improvements with shedded systems | 2. UNE - confirming speaker between Peter or Angela Lees now at UQ | Dr Angela Lees Lecturer in Animal Production Science School of Agriculture and Food Sciences University of Queensland a.lees@uq.edu.au | Industry best practice, whats next?
| 3. Rangers Valley | Alex Smith Feedlot Manager Rangers Valley Feedlot | New innovation and technology
| 4. AGDSA | Matt Norton Director AG DSA 0418 446 245 matt.norton@agdsa.com.au
Platforms and systems Carbon explained
| 1. Equipoise – | Alan Key Managing Director Equipoised Group and Earthtrade | Producer example, already implementing and are market forces increasing awareness
| 2. Compass - | Simon Jackson, Head of CSR - Compass Group Australia
Demystifying carbon markets and net zero! | 3. Stockyard | Molly Sage - Sustainability Officer Stockyard Lot Feeders Pty Ltd Email: molly@stockyardbeef.com.au Web: www.stockyardbeef.com.au 236 Jondaryan Evanslea Road | Marsh – ESG rating methodology
| 4. Futurefeed | Louise Robb Carbon Program Manager louiser@futurefeed.com.au mob +61 459225644 future-feed.com Gasworks, Tower A. Level 2, 76 Skyring Terrace Newstead, QLD 4006, Australia | Insurance market is shifting Property portfolio, ESG outlook impacts.

## RSVP
Member | First Name | Surname | Company | Email address | Dietary

## Speaker
First Name | Surname | Company
Cameron | Best | Mort & Co
Scott | Braund | Mort & Co
Steve | Budden | Optimal Group
Bryce | Camm | Camm Agricultural Group
Sam | Churchill | JBS
Jodie | Courtice | McLean Farms
Sharon | Denny | ReThink Sustainability
Niki | Ford | Australian Organic Ltd
Andrew | Gray | Animal EyeQ
Natalie | Hick | Australian Sustainable Food Company
Simon | Jackson | Compass Group Australia
Thomas | Key | Earthtrade
Dr Angela | Lees | University of Queensland
Professor Bernadette | McCabe | Centre for Agricultural Engineering
Greg | McCalman | Entegra
Bruce | McConnel | FarmedWell Ltd
Joseph | McMeniman | Meat and Livestock Australia
David | McNab | Department of Agriculture, Fisheries and Forestry
Matt | Norton | AgDSA
Jemma | Postle | APIAM Animal Health Vet
Stuart | Pratt | Wasco Energy
Louise | Robb | Futurefeed
Molly | Sage | Stockyard
Alex | Smith | Rangers Valley
Dr Robert | van Barneveld | SunPork Group

## Media
FIRST | LAST | BUSINESS
Harry | Clarke | Country Caller
Caitlin | Crowley | Country Caller
Jessica | Clarke | Argus Media
James | Nason | Beef Central
Amy | Phillips | ABC Country Hour
Arlie | Felton-Taylor | ABC Country Hour
Billy | Jupp | Queensland Country Life
Eric | Barker | Beef Central
`